## Sheet1
Requirement ID | Description | Story Points | Priority | Sprint
1 | Frontend form - searchable fields - rating, genre, date, name | 3 | 1 | 1 | complete 10/27/24
2 | Search button, query to linked database | 5 | 1 | 1 | complete 10/27/24
3 | List of movies - search results | 2 | 1 | 2
4 | User Account creation: username, password | 3 | 2 | 2
5 | User Account - User Lists | 2 | 2 | 2
6 | Soundtrack link - Spotify | 5 | 3 | 3
7 | search movie soundtracks from frontend form | 3 | 3 | 3
8 | connection to Spotify | 5 | 3 | 3
9 | Website UI Design | 13 | 2 | 1 | complete 10/27/24
10 | FInalize Frontend Design | 5 | 1 | 2
11 | Finalize Website Architechture | 8 | 1 | 3
12 | Movie Poster Graphics Added | 3 | 3 | 3
13 | Add Searchable field: Currently Available On (Streaming Service) | 2 | 3 | 2
14 | User Account - Random Movie Selector | 2 | 2 | 3
15 | add streaming service to users | 5 | 3 | 3